TEMPLATE 1: SUMMARY

Company Name: Sustainow Technologies Private Limited

Name of solution (if different from the company): KlimaGuard Kids

Country of Registration: India

Provide a summary of the solution (200 characters limit): Open-source agentic AI that turns live climate/AQ into age-banded child health preparedness guidance + India CHIS scores for schools, CHWs, and programmes.

At what stage is your solution?
☑ Early stage (Working prototype with initial testing or pilots)
☐ Deployment ready stage

☑ Early stage (Working prototype with initial testing or pilots)

☐ Deployment ready stage (Proven solution that is deployment ready...)

Is your company is women-founded or women-led?

(A female-founded or female-led company is characterized by having a woman as a founder or co-founder who actively participates in the company's decision-making processes. This active role may involve serving in an advisory capacity for key decisions, demonstrating a commitment to the strategic direction of the business. It is important to note that active involvement does not necessarily demand a full-time role, but rather a meaningful and influential contribution to the company's leadership and direction.)

☑ Yes

☐ No

If yes: Purushothaman Manjula Devi — Co-Founder & Director. She co-founded the company (DIN director since incorporation 12-03-2025) and actively leads product strategy, partnerships, and impact decisions.

# Part 1: Summary

Please complete all your responses within the fields provided.

- What is the core problem you want to solve through your solution? (1,000 characters limit)

Climate change intensifies heatwaves, floods, air pollution, vector-borne disease, and food insecurity. Children are disproportionately harmed by physiology, caregiver dependence, and disruption to school and nutrition. Most climate tools target policymakers; few deliver actionable, age-appropriate preparedness guidance that frontline workers, teachers, and caregivers can use within hours. Without child-centred early warning that links live climate signals to health, nutrition, and disease risk—especially in climate-vulnerable cities and Indian districts—communities react late, after clinics fill and learning time is lost.

- How does your solution solve this core problem? (1,000 characters limit)

KlimaGuard Kids is an open-source (MIT), agentic web platform that turns live Open-Meteo weather/AQ into child-centred preparedness guidance via eight transparent TypeScript agents (climate, health, nutrition, disease, natural medicine, India regional, India CHIS impact, synthesis). It covers 159 countries, 482 Tier 1–3 cities, and 77 India regions with a measurable Child Health Impact Score (0–100). Outputs include caregiver briefings, age-banded cards (5–8 / 9–12 / 13–17), and kids play missions—without requiring child accounts. Provenance cites ~50 validated sources (WHO/UNICEF/UNDRR, FAO/IPC, Copernicus, India IMD/NFHS, etc.).

- Describe the results of your user testing/prototyping. Please provide a detailed response on who your main users are and the quantitative and qualitative results of the testing to date) (1,000 characters limit)

Main users: caregivers, teachers, community health workers, NGO/CSR programme staff, and supervised youth. Prototype status: working production-style Next.js app with live climate fetch, full agent pipeline, India CHIS dashboard, global city selector, and age-banded play. Internal demo reviews across diverse climates show end-to-end analysis typically completing in seconds; stakeholders rate unified climate–health briefings clearer than siloed weather/health alerts. Registry stress-tested across 159 countries / 482 cities / 77 India regions. Formal field pilot with ministries/schools is planned for the investment period (target ≥3 partner sites, ≥500 guided sessions) to quantify comprehension and preparedness behaviour change.

- Describe the value that you deliver to the users of your technology  (1,000 characters limit)

Users receive location-specific climate–health intelligence they can act on the same day: heat/flood/air/vector stressors, hydration and food-safety notes, disease precautions, and age-appropriate guidance. Schools get classroom-ready messaging and play missions; CHWs get briefings before peak seasons; programme officers get transparent CHIS scores for regional prioritisation. Open MIT licensing lets UN entities and governments audit, fork, and deploy in-country without proprietary lock-in. APIs (/api/analyze, /api/countries, /api/india/regions) support integration into partner systems.

If your solution has climate and health-related impact, please specify the relevant climate-health outcomes.

Anticipatory reduction of child heat stress, respiratory burden from poor AQ, waterborne/vector disease pressure, and climate-linked nutrition stress. Measured via CHIS dimensions (CHVI, CRBS, WDPI, VBDP, CNSI) and age-banded preparedness actions. Aligns with SDG 3, 13, 2, 4, and 11.

- Outline the three main objectives for which potential funding from UNICEF will be used:

1) Evidence generation: structured school/CHW pilots in ≥3 climate-vulnerable sites with baseline/endline preparedness metrics and public evaluation brief.
2) Product hardening for UNICEF-scale use: multilingual UI (≥3 languages), accessibility, offline-capable PWA, optional national met/AQ feed adapters, privacy review.
3) Open-source ecosystem & interoperability: expanded registries, documented APIs, contributor onboarding, and pathways to DHIS2/partner dashboard integration.

- What are the expected outcomes/results of the 12-month investment period? Also share how you intend to showcase evidence of impact: (1,000 characters limit)

Outcomes: (a) validated pilot evidence pack (usage, comprehension, preparedness actions) from ≥500 sessions; (b) production-hardened release with 3 languages + PWA offline shell; (c) public OSS milestones and real-time investment data dashboard. Evidence: quarterly KPI reports, anonymised aggregate analytics, partner testimonials, open GitHub releases, and a final public evaluation note suitable for UNICEF Venture Fund learning.

- Please list the three main risks you anticipate for the success of your project. Outline the steps you will take to mitigate them (500 characters limit per field)

| Risk (description) | Level of risk (high, low) | Probability (high, low) | Action planned to mitigate |
| --- | --- | --- | --- |
| Pilot adoption delay (schools/CHW bandwidth) | Medium | Medium | Pre-commit ≥3 partner sites; lightweight 20-min training; offline PWA fallback |
| Heuristic guidance misread as clinical advice | High | Low | Clear non-diagnostic disclaimers; caregiver/CHW framing; safeguarding review |
| Upstream Open-Meteo/API outage | Medium | Low | Cached last-good snapshots; optional national met adapters; status banners |

- Does your solution have any established evidence of health outcomes, safety, or efficacy? Provide details of completed studies, pilots, evaluations, or real-world deployments, including methodology, sample size, location, dates, outcomes measured, and results. Please attach or provide links to any published reports, evaluation documents, or peer-reviewed publications, if available.

Current evidence is prototype/demo-level: functioning open-source platform with transparent heuristics (not a medical device). No peer-reviewed clinical efficacy trial yet. Investment will fund formal pilots with defined methodology, sample size, and ethics-appropriate protocols. Live demo: https://klimaguardkids.sustainow.in/ · Source: https://github.com/carbonintelli/KlimaGuardKids · Technical commendation: docs/KGK_Technical_Commendation.pdf in repository.

- Does your solution currently comply with, integrate with, or support any recognized digital health standards or interoperability frameworks? (e.g., HL7 FHIR, DICOM, IHE, ICD-10/11, SNOMED CT, LOINC, OpenHIE, DHIS2, OpenMRS). For each standard referenced, please indicate whether it is currently implemented, partially implemented, planned, or under evaluation.

Currently: JSON REST APIs for analysis and geographic registries (custom schema). Planned under investment: DHIS2 interoperability evaluation/partial implementation for aggregate indicators; ICD-11 tagging under evaluation for disease outlook categories; HL7 FHIR observation mapping under evaluation for future EHR-light exports. Not a clinical records system today.

# Part 2: Product Pitch

Please prepare and provide a short video to pitch your technology and introduce your project team. The video must follow the specifications below:

- Maximum of 2 minutes

- The video must show and demonstrate:

  - a functioning prototype (e.g. walk-through of the solution, screenshots of interfaces)

  - team members and their roles

  - main three revenue streams and why it’s going to work

The video must be uploaded to YouTube and cannot be edited after the submission deadline.

Link to video: [TO ADD — YouTube 2-min pitch URL before e-submission]

Password to view (if applicable): N/A (public link when uploaded)