## Project Design and Data Plan
TEMPLATE 3 Tab 1: PROJECT DESIGN STATEMENT
Company name: | Sustainow Technologies Private Limited
Note: it is mandatory to complete columns C-F for each Activity you propose. Incomplete project designs will not be scored.
Timeline | Tasks | Expected Changes/Targets | Signs of Success | What data will be generated? | Key Personnel Responsible
|  | What will be different once the activity is done? (Provide specific numbers where possible.) | What will you measure to assess whether the activity was completed and the desired outcome achieved? Please specify the numeric targets for your expected outcomes (e.g., number of users). Each activity must have at least one measurable outcome. | Each activity needs to generate specific types of data. For example: (1) During software development, there may be GitHub commits or version control logs; during content creation, the volume of digital materials will increase. (2) During piloting, you can track user numbers, user feedback, and updates to code or design. (3) During implementation, you can monitor new user registrations or deployment progress via online tracking tools. We require each activity to produce real-time data that is accessible through internet-based tools (e.g., dashboards, trackers, APIs). Please indicate what data will be generated per activity, how it will be collected, and how it will be accessed. | Who is responsible for each task? Refer to the funding agreement for the definition of 'Key Personnel' and details on who may be included. Name and role in the team.
Quarter 1
Milestone 1
Activity 1 | M1: Pilot site MoUs & ethics-light protocol | ≥3 sites committed | Signed partner briefs | MoU dates, site list | Manjula Devi
Activity 2 | Partner onboarding packs (schools/CHWs) | Training kit v1 live | ≥6 facilitators trained | Training attendance | Manjula Devi
| Baseline preparedness survey design | Survey instrument locked | IRB/ethics note filed if needed | Survey schema | Manjula Devi
Milestone 2 | M2: Multilingual foundation | i18n framework shipped | EN+HI+1 language scaffolding | Locale coverage metrics | Nandagopal Govindan
Activity 1 | String extraction & translation workflow | ≥80% UI strings externalized | L10n PRs merged | String coverage % | Nandagopal Govindan
Activity 2 | Accessibility pass (WCAG 2.1 AA targets) | Critical a11y issues <5 | Axe CI report green | A11y issue counts | Nandagopal Govindan
| M3: Real-time investment data feed | Public KPI endpoint | Dashboard shows live KPIs | KPI time series | Nandagopal Govindan
Milestone 3 | Anonymised usage analytics (no child PII) | Event pipeline live | ≥95% events schema-valid | Event volumes | Nandagopal Govindan
Activity 1 | M4: Registry & sources expansion | +10% Tier-3 cities | Release tag v0.4 | City/source counts | Nandagopal Govindan
Activity 2 | India CHIS validation notes with experts | Expert review memo | ≥3 expert reviews | Review comments | Manjula Devi
Milestone 4 | User testing Product/UX (Q1) | ≥50 guided sessions | SUS/comprehension scores | Session logs, scores | Manjula Devi
Activity 1 | User testing UI (Q1) | UI issues backlog triaged | Top 10 UX fixes shipped | Issue tracker | Nandagopal Govindan
Activity 2
| Q1 FE deliverables | i18n shell + a11y fixes | Tagged release | Release notes | Nandagopal Govindan
Milestone 5 | Q1 BE deliverables | KPI/analytics APIs | Uptime >99% demo | Uptime, latency | Nandagopal Govindan
Activity 1 | User testing (Product and UX)
Activity 2 | M1: PWA offline shell | Offline guidance cache | Lighthouse PWA ≥80 | Cache hit rates | Nandagopal Govindan
| Service worker & last-good climate cache | Graceful offline mode | Offline demo script pass | Offline test results | Nandagopal Govindan
Q1 Key Deliverables | M2: National met/AQ adapter interface | Adapter interface v1 | 1 national feed stub | Adapter docs | Nandagopal Govindan
Front-end | IMD/CPCB reference integration notes | India feed design doc | Partner technical review | Design doc | Nandagopal Govindan
Backend | M3: School pilot wave 1 | ≥200 sessions completed | Attendance & completion % | Pilot dataset | Manjula Devi
| CHW briefing workshops | ≥40 CHWs oriented | Workshop feedback ≥4/5 | Feedback forms | Manjula Devi
Quarter 2 | M4: DHIS2 interoperability spike | Feasibility report | Go/no-go decision | Spike report | Nandagopal Govindan
Milestone 1 | Aggregate indicator mapping | Draft indicator dictionary | Reviewed by partner M&E | Indicator list | Manjula Devi
Activity 1
Activity 2 | User testing Product/UX (Q2) | ≥100 cumulative sessions | Improved task success ≥15% | UX metrics | Manjula Devi
| User testing UI (Q2) | Mobile UX hardened | Mobile crash-free >99% | Mobile analytics | Nandagopal Govindan
Milestone 2
Activity 1 | Q2 FE: PWA + mobile UX | PWA in production demo | Release v0.5 | Release notes | Nandagopal Govindan
Activity 2 | Q2 BE: adapters + analytics | Adapter + KPI stable | Latency p95 <3s | Perf metrics | Nandagopal Govindan
Milestone 3
Activity 1
Activity 2
Milestone 4
Activity 1
Activity 2
Milestone 5 | Validation and feedback (If applicable) | (specify number of users testing your solution)
Activity 1 | User testing (Product and UX)
Activity 2 | User testing (UI)
Q2 Key Deliverables
Front-end
Backend
Quarter 3
Milestone 1 | M1: Midline evaluation | Midline report published | Report accepted internally | Midline dataset | Manjula Devi
Activity 1 | Comparative site analysis | Cross-site insights | ≥3 sites compared | Comparison tables | Manjula Devi
Activity 2
| M2: Language pack completion | 3 languages complete | Linguist QA sign-off | L10n QA log | Nandagopal Govindan
Milestone 2 | Community OSS contributor sprint | ≥5 external PRs | Contributor guide live | PR/contributor counts | Nandagopal Govindan
Activity 1
Activity 2 | M3: Safeguarding & privacy review | Review checklist complete | Remediations merged | Review report | Manjula Devi
| Child-data policy pack | Policy docs published | Legal review note | Policy PDFs | Manjula Devi
Milestone 3
Activity 1 | M4: Partner integration pilots | 1 partner API integration | Successful sandbox calls | Integration logs | Nandagopal Govindan
Activity 2
Milestone 4
Activity 1 | User testing Product/UX (Q3) | ≥300 cumulative sessions | Preparedness score ↑ | Survey results | Manjula Devi
Activity 2 | User testing UI (Q3) | Localization UX validated | Language switch success ≥95% | UX tests | Nandagopal Govindan
Milestone 5 | Validation and feedback (If applicable) | (specify number of users testing your solution)
Activity 1 | User testing (Product and UX)
Activity 2 | User testing (UI)
Q3 Key Deliverables
Front-end
Backend
Quarter 4
Milestone 1 | M1: Endline evaluation & public brief | Public evaluation brief | Brief on GitHub/site | Endline data | Manjula Devi
Activity 1 | UNICEF learning package | Case study delivered | VF learning assets | Case study doc | Manjula Devi
Activity 2
| M2: Scale-ready release v1.0 | Tagged v1.0 OSS release | CI green; docs complete | Release artifacts | Nandagopal Govindan
Milestone 2 | Deployment playbook (gov cloud) | Playbook published | Partner can redeploy | Playbook PDF | Nandagopal Govindan
Activity 1
Activity 2 | M3: Growth Funding / LTAS readiness | Pipeline of follow-ons | ≥3 follow-on conversations | Pipeline CRM notes | Manjula Devi
| Business model validation update | Updated unit economics | Board/director review | Financial memo | Manjula Devi
Milestone 3
Activity 1 | M4: Knowledge transfer & handoff | Training recordings | Partners self-serve | Training assets | Both directors
Activity 2
Milestone 4
Activity 1 | Final UX validation (≥500 sessions) | Session target met | Final KPI dashboard | Full pilot dataset | Manjula Devi
Activity 2 | Final UI polish & accessibility | AA critical issues closed | A11y audit archive | Audit report | Nandagopal Govindan
Milestone 5 | Validation and feedback (If applicable) | (specify number of users testing your solution)
Activity 1 | User testing (Product and UX)
Activity 2 | User testing (UI)
Q4 Key Deliverables
Front-end
Backend
List all new product features that will be developed in the one-year investment period
Please list all Open Source components generated through the workplan
Please list any proprietary components developed though the workplan
Note on A5: Administrator: Include as many milestones and activities as you need to keep the consistency along the project design.